## Contact Info
Name | Phone | Email | Scrumboard | Github
Sean Woods | 408-444-0648 | srwoods@ucsc.edu | https://trello.com/b/5uzWWJz7/squadup-scrum-board | https://github.com/BigerBallers/SquadUp
Zahir Yahya | 831-706-0607 | zyahya@ucsc.edu | https://trello.com/b/5uzWWJz7
Chuangbo Tong | 408-594-5253 | ctong3@ucsc.edu
Shyaan Khan | 510-589-9791 | skhan17@ucsc.edu | Slack
Collin Fulcher | 951-634-4701 | cfulcher@ucsc.edu | https://squadupworkspace.slack.com/
Tyler Frick | 415-933-0915 | tfrick@ucsc.edu

## Sprint 1
Person | User Story | Task | Date Est. | Date Actual | Time Est. | Time Actual | Status | Notes | Roadblocks
Shyaan/Phillip | 1 | Mock up design for the front end. | 2018-07-09 | 2018-07-09 | 3 | 4 | Completed
Zahir | 1 | Set up the database, MongoDB | 2018-07-09 | 2018-07-09 | 1 | 1 | Completed
Zahir | 1 | Set up Mlab | 2018-07-09 | 2018-07-09 | 1 | 1 | Completed
Sean | 1 | Researching how to create a REACT web application. | 2018-07-09 | 2018-07-09 | 2 | 1 | Completed
All members | 1 | Troubleshooting local server initialization for all members. | 2018-07-09 | 2018-07-09 | 2 | 3 | Completed | Sean - Troubleshooting my end so far has taken 1 hour.
Tyler/Zahir | 1 | Set up node.js and express with server. Server: localhost:8080 | 2018-07-09 | 2018-07-09 | 1 | 1 | Completed | Needs to be finished for linking google accounts.
Sean | 1 | Create the front end REACT server: localhost:3000 | 2018-07-09 | 2018-07-05 | 1 | 1 | Completed
Tyler | 2 | Look into Github hosting | 2018-07-09 | 2018-07-09 | 1 | 1 | Completed | wont go this route
All members | 0 | Scrum Meeting | 2018-07-05 | 2018-07-05 | 0 | 0 | Completed | First scrum meeting at TA session. | Google api, templates for the frontend, figuring out setup from backend to frontend, researching api, website react
Zahir/Tyler | 1 | Link the user google account with DB. | 2018-07-09 | 2018-07-09 | 3 | 8 | Completed | Done after DB setup.
Zahir/Shyaan | 1 | Create a Database Schema | 2018-07-09 | 2018-07-09 | 3 | 3 | Completed | created basic schema. can always add to it
Collin | 2 | Create a home page | 2018-07-09 | 2018-07-09 | 1 | 7 | Completed
Collin | 1 | Create a front end page to host the account log in. | 2018-07-09 | 2018-07-09 | 1 | 7 | Completed | Wait for node.js and express
Sean | 2 | Create Park Finder page | 2018-07-09 | 2018-07-09 | 2 | 4 | Completed | Researching REACT, passed to phillip as the google maps API task. Moved to gatsby library.
All members | 0 | Scrum Meeting | 2018-07-09 | 2018-07-09 | 0 | 0 | Completed
Phillip | 2 | Create an add park page/form | 2018-07-09 | 2018-07-09 | 1 | 1 | Completed
Sean | 2 | Create an account holder page | 2018-07-09 | 2018-07-09 | 1 | 1 | Completed
Sean | 2 | Create an event page/form | 2018-07-09 | 2018-07-09 | 1 | 1 | Completed
Phillip | 3 | Use the google maps API to be able to search for parks. | 2018-07-09 |  | 2 | 0 | Completed
Zahir | 1 | Restrict API calls to authorized users |  |  | 3 | 8 | In Progress
Sean | 3 | Test search functionality of the google maps API. | 2018-07-09 |  | 1 | 0 | Not Started | not implemented | Need to have page and API implemented.
[5 empty] | 27 | 45

## Sprint 2
Person | User Story | Task | Date Est. | Date Actual | Time Est. | Time Actual | Status | Notes | Roadblocks
Zahir/Collin | 1 | Link the Google Authentication page with the landing page after you log in. | 2018-07-16 | 2018-07-11 | 2 | 2 | Completed | Zahir working on using front end method, Collin working on back end method | REACT Roadblocks
Zahir/Collin | 1 | Create a basic button that links with Google Authentication on the page. | 2018-07-16 | 2018-07-11 | 1 | 1 | Completed
Sean/Tyler | 1 | Create a link for every page being used. | 2018-07-16 | 2018-07-11 | 2 | 2 | Completed
Sean/Tyler | 1 | Test retrieving data from MongoDB and displaying it on the page. | 2018-07-16 | 2018-07-11 | 5 | 3 | Completed | JSON data shows in consol log. | Merging the changes.
Shyaan | 2 | Implement the Google Map API on the maps page | 2018-07-16 | 2018-07-11 | 2 | 2 | Completed | Need actual hours done on this task --
All Members | 0 | Scrum Meeting | 2018-07-11 | 2018-07-11 | 0 | 0 | Completed
Collin/Sean | 1 | Created a continue button that links to website after logging in. | 2018-07-16 | 2018-07-12 | 2 | 2 | Completed
Tyler | 2 | Send park data from database onto maps page | 2018-07-16 | 2018-07-12 | 2 | 2 | Completed
Philip | 1 | Finish Add Park page, combining with Gatsby and finish styling | 2018-07-13 | 2018-07-13 | 3 | 7 | Completed | Gatsby styling was kind of strange and I commented on the style page to address the issue, takes longer than I thought (UPDATE: Collin helped make the page more readable for the time being)
Collin/Sean | 2 | Add elements to banner for user name and logout. | 2018-07-16 | 2018-07-16 | 3 | 6 | Completed |  | Gatsby roadblock for the header page. How do we add more elements within this header?
Shyaan/Phillip | 1 | Test sending information from Page to DB. | 2018-07-16 | 2018-07-16 | 4 | 4 | Completed
Tyler | 2 | Create events database. | 2018-07-16 | 2018-07-16 | 2 | 2 | Completed
All Members | 0 | Scrum Meeting | 2018-07-12 | 2018-07-12 | 0 | 0 | Completed
All Members | 0 | Scrum Meeting | 2018-07-16 | 2018-07-16 | 0 | 0 | Completed
Shyaan/Phillip | 1 | Create a logout button that works. | 2018-07-16 |  | 4 | 5 | Completed
All Members | 0 | Version Control merging all branches into master that are working. | 2018-07-16 |  | 8 | 6 | Completed | Sean/Collin merged all gatsby and are restructuring the pages folder to be better organized -- 2 hours.
| 2 | Create ArrayList to view the events. Look into options. | 2018-07-16 |  | 6 |  | Not Started
| 2 | Read in JSON data and use it on the Google Map API. | 2018-07-16 |  | 5 |  | Not Started
[5 empty] | 51 | 44

## Sprint 3
Person | User Story | Task | Date Est. | Date Actual | Time Est. | Time Actual | Status | Notes | Roadblocks
Shyaan | 1 | Fix login page | 2018-07-23 | 2018-07-17 | 1 | 1 | Completed
Phillip | 1 | Implement an add-event page | 2018-07-23 | 2018-07-21 | 3 | 3 | Completed
Tyler | 2 | Get event by ID,from the DB info | 2018-07-23 | 2018-07-18 | 2 | 2 | Completed
Tyler/Zahir | 2 | Get events user is attending | 2018-07-23 | 2018-07-18 | 2 | 4 | Completed
Tyler | 2 | Get all parks by category | 2018-07-23 | 2018-07-18 | 1 | 1 | Completed
Zahir | 2 | Get parks by radius | 2018-07-23 | 2018-07-18 | 1 | 1 | Completed
Tyler | 2 | Get all events at park | 2018-07-23 | 2018-07-19 | 1 | 1 | Completed
Phillip | 1 | Allow user to select multiple sports when adding park | 2018-07-23 | 2018-07-22 | 2 | 2 | Completed
Tyler/Zahir | 2 | Get all parks user is following | 2018-07-23 | 2018-07-20 | 1 | 1 | Completed
Sean | 1 | Implement an account profile page | 2018-07-23 | 2018-07-24 | 5 | 11 | Completed
Collin | 1 | Implement an event list page | 2018-07-23 | 2018-07-24 | 5 | 7 | Completed
Phillip/Collin/Sean | 1 | Change landing page to be closer to mockup | 2018-07-23 | 2018-07-24 | 2 | 1 | Completed
Shyaan | 1 | Create search/map page | 2018-07-23 | 2018-07-20 | 6 | 6 | Completed
Shyaan??? | 1 | Implement a park view page. 2 Buttons, 1 List | 2018-07-23 | 2018-07-24 | 6 | 6 | Completed
Tyler/Zahir | 3 | Test backend API calls | 2018-07-23 |  | 4 | 3 | In Progress
All | 3 | Test each page individually | 2018-07-23 |  | 4 | 5 | In Progress
[5 empty] | 46 | 55

## BurnUp Sprint 1
Dates | Estimated Hours Completed | Actual Hours Completed | Sprint Total Hours | Key
2018-07-02 | 0 | 0 | 22 | Red | Actual hours
2018-07-05 | 18 | 21 | 27 | Blue | Estimated hours
2018-07-09 | 24 | 45 | 27 | Yellow | Total estimated hours

## BurnUp Sprint 2
Dates | Estimated Hours Completed | Actual Hours Completed | Sprint Total Hours | Key
2018-07-09 | 0 | 0 | 35 | Red | Actual hours
2018-07-11 | 10 | 8 | 35 | Blue | Estimated hours
2018-07-12 | 19 | 24 | 51 | Yellow | Total estimated hours
2018-07-16 | 40 | 44 | 51

## BurnUp Sprint 3
Dates | Estimated Hours Completed | Actual Hours Completed | Sprint Total Hours | Key
2018-07-16 | 0 | 0 | 45 | Red | Actual hours
2018-07-18 | 11 | 15 | 45 | Blue | Estimated hours
2018-07-23 | 26 | 35 | 46 | Yellow | Total estimated hours
2018-07-24 | 38 | 55 | 46

## BurnUp- All sprints
Dates | Estimated Hours Completed | Actual Hours Completed | Sprint Total Hours | Key
2018-07-09 | 24 | 45 | 27 | Red | Actual hours
2018-07-16 | 64 | 89 | 78 | Blue | Estimated hours
2018-07-24 | 102 | 144 | 124 | Yellow | Total estimated hours